## Slide 1: Title and Total Compensation Project (TTC) Academic Staff Assembly February 10, 2020
Mark Walters, Chief Human Resource Officer
Diane Blaskowski, Talent Rewards Director

## Slide 2
Employee Mapping w/ Division HR
Compensation/Title Structure Finalization
Review and Evaluate Benefits Strategy
Develop Benefits Recommendations
Standardized Job Titling and Comp Structure
Campus
Partnership
Benefits
SJD Library Posted
SEP
OCT
NOV
JUN
MAY
APR
MAR
FEB
JAN
DEC
JUL
AUG
SEP
Letter Notification
Campus Forums
HR Training
Manager Training
Employee/Manager Engagement
Employee Communications & Training Offering
Campus Forums
Title/SJD Appeals Process
Employee
OHR
Campus Forums
Benefits Implementation Strategy
Long-term Compensation
Implementation Strategy
TTC QA: SJD Consistency, Review mapping
(Phases I & II)
TTC QA: Ongoing (Phase III)
Salary Structure Training
TTC Project Timeline

## Slide 3: Key Dates – Timeline Shift
February 2020
Complete Quality Assurance (QA) phases I & II
April 2020
Employee Conversations conclude (part of QA phase III)
May 2020
Salary structure available
Notification letters sent to staff (translated copies available)
Appeals process begins
July 1, 2020
New titles and salary structure go into effect

## Slide 4: QA Goals
Create consistent mapping across campus:
  Hold divisional alignment sessions
  Identify trends, outliers and evaluate for accuracy
  Review mapping by job groups (e.g. leadership)
  Address manager and employee concerns
Standardize the Title and Standard Job Description (SJD) Library:
  Align job summaries with essential duties
  Confirm each jobs has appropriate Fair Labor Standards Act (FLSA) status
  Identify gaps

## Slide 5: QA Updates
February 2020:
  Today, 65 percent of QA is complete
  Goal: all employees have QA Complete status
  Employee conversations for all titles can begin
March 1, 2020:
  Updates to existing SJDs will be finalized
April 30, 2020:
  All employee conversations and position descriptions will be complete

## Slide 6: Employee Conversations
Conversations Include
New official job title
New business title/working title
New position description
Next steps
Conversations Do Not Include
Salary range of new title
Changes to benefits package
Goal:
Confirm that new titles and position descriptions accurately describe the work employees do
Note: Employees can still appeal their title after having a conversation

## Slide 7: Conversations
  All Conversations:
  Provide an opportunity for employees to ask questions
  Conclude by April 30, 2020
  Formats Vary Across Campus:
  Could occur in a group or one-on-one
  Led by HR or managers
  May include multiple conversations

## Slide 8: Managers Prepare for Conversations
Online Manager Training:
Describes the manager role in TTC Project
1,444 have registered or completed training
Manager Conversation Practice (Supplemental):
Prepares managers for employee conversations
Focuses on listening and responding to employees
More than 50 in-person sessions available through April

## Slide 9: February Forums
Topics:
Learn about the updated project timeline
Find out about progression and promotion
Get information about official title notification letters and appeals
Bring your questions

## Slide 10: February All-Campus Forums
Dates | Location | Event Time
2/11/2020 | Gordon Dining & Event Center (Multilingual)/Daytime | 1:30 – 3 p.m.
2/12/2020 | Gordon Dining & Event Center (English Only)/Daytime | 1– 2:30 p.m.
2/12/2020 | Health Sciences Learning Center (Multilingual)/Late Night | 11 p.m.– 12:30 a.m.
2/17/2020 | Gordon Dining & Event Center (English Only)/Daytime | 1– 2:30 p.m.
2/18/2020 | Health Sciences Learning Center (English Only)/Daytime | 1– 2:30 p.m.
Notes: MBG

## Slide 11: February All-Campus Forums
Dates | Location | Event Time
2/19/2020 | Memorial Union (English Only)/Daytime | 9 – 10:30 a.m.
2/20/2020 | Health Science Learning Center (English Only)/Daytime | 10:30 a.m. – 12 p.m.
2/26/2020 | Online Forum (English Only)/Daytime | 11 a.m. – 12:30 p.m.
Notes: MBG

## Slide 12: Learning Opportunities & Resources
Fact sheets
Learning series
Videos
Frequently Asked Questions
Online modules

## Slide 13: Where To Turn?
Employee Assistance Office & LifeMatters
Confidential workplace consultation for employees and managers
Career and Education Planning through the Division of Continuing Studies
Counseling on career exploration and planning
Ombuds Office
Confidential guidance on workplace concerns
Professional Development courses
Courses on communication and managing change

## Slide 14: Benefits Summary Reports: Online
hr.wisc.edu/title-and-total-compensation-study/resources/

## Slide 15: TTC Project Website
go.wisc.edu/TTCProject

## Slide 16: Questions
Website:
go.wisc.edu/ttcproject
Email: ttcstudy@ohr.wisc.edu